## Sheet1
| 2026-03-23 | 2026-03-30 | 2026-04-06 | 2026-04-13 | 2026-04-20 | 2026-04-20 | 2026-04-27 | 2026-05-04 | 2026-05-05
basic steps
github repo setup + desc
opensource models selection
testing approaches selection
script for onpremise testing demo
system prompt
unified system prompt
script for testing demo
script for target testing
aggregating results
judging results
system prompt + fine tuning
dataset preparation
fine tuning process
aggregating results
judging results
final presentation
results analysis
presentation file
live demo ssh wrapper?
project delivery